## Sheet1
Sr No | Day | Date | Task | Description
1 | Day 1 | 2026-09-19 | Github Repo | Create Github Repo and clone to local desktop
2 | Day 2 | 2026-09-19 | LLM Key exploration & Set up | Explore the diff way to get LLM API keys
3 | Day 3 | 2026-09-23 | Project scaffolding | .yaml, gitignore….......
4 | Day 4 | 2026-09-24 | Project folder scaffolding (other than root)
5 | Day 4 | 2026-09-24 | Rag Implementation SOW
6 | Day 5 | 2026-09-25 | Rag Implementation - DB Se up
7 | Day 7 | 2026-09-28 | Rag - Eval Harness and Questions
8 | Day 8 | 2026-09-29 | Nl2SQL Implementation
9 | Day 9 | 2026-09-30 | RAG + NL2SQL Integration
10 | Day 9 | 2026-09-30 | Single agent vs Agentic Implementation | treat rag and NL2SQL as diff tool to treat as agentic ai vs single agent
11 | Day 10 | 2026-10-07
12
13
14
15
16
Formulas:
Date = [Date, row above]+1

## Features
Module | Feature | Tech Details
RAG | Upload PDF
Add new PDF
| Delete old PDF, related to new pdf | Don’t reembed full document, only do which portion got updated - tracking which vector IDs belong to which source document
| Check duplicacy of PDF while uploading | content hash (SHA-256)
I agent pick info, which is wrong then agent reditect to human to review, update the vector - selfheal AI