Capstone Project Plan

Three-in-One GenAI Chatbot — Week-by-Week Build Roadmap

RAG Chatbot with HITL  |  Database Chatbot (NL2SQL)  |  Session File Upload  |  Redis  |  JWT  |  CI/CD  |  Observability

Solution Architect Learning Reference

Enterprise AI Delivery Playbook  —  System Design Series

Prepared for: Sachin Rathi

# How to Use This Document

This document is a hands-on capstone project plan, following the theory-heavy System Design Study Series. It is structured to turn the project brief into a concrete, sequenced build — starting with the simplest working piece and layering in complexity, exactly as requested, rather than attempting everything at once.

The document is organized in four parts: (1) an honest analysis of the project as scoped, including how it maps back to the six-bucket roadmap from earlier in this series; (2) the recommended build order and the reasoning behind it; (3) a week-by-week schedule with concrete, checkable deliverables for each week; (4) a set of good-to-have additions, each tagged with which week it fits into and which prior document in this series it draws on.

# Section 1 — Project Analysis

The Brief

I have almost finished the learning path for GenAI and now want to implement a project on my own to concrete my learning — a chatbot. (1) RAG-based chatbot: users can ask questions from KBs; a pipeline to add, update, and delete KBs at the backend; a flow where users give feedback on responses (HITL) and the chatbot acts on it — self-heal AI. (2) Database-based chatbot: users ask questions from a database, the LLM uses a semantic model to generate a query, gets data, and gives a response back. (3) Self-upload at session level: the user can upload a file and ask to perform an action like summarizing the document, extracting information, or saving it to a database. Use Redis for caching, JWT tokens for authentication. Build a CI/CD pipeline from push-to-main to deploy on AWS or any cloud. Set up logging (CloudWatch), monitoring, and observability (LangSmith). I will not build this from day 1 — I will pick the easiest part first and proceed to the final build.

## 1.1  Overall Verdict

This is a genuinely strong, well-scoped capstone project — it is not a toy exercise. It deliberately touches nearly every bucket from the Complete Roadmap document earlier in this series: Architecture (three distinct chatbot patterns, Redis, auth), Cloud/DevOps (CI/CD, AWS deployment), Data/RAG Pipeline (KB ingestion), LLM Engineering (feedback loop, semantic-model query generation), and Backend/FastAPI (the layer tying it all together). Completing this project end to end would be a legitimate, defensible portfolio piece to discuss in an RFP technical conversation or a client architecture review.

## 1.2  The Three Sub-Projects, Honestly Ranked by Difficulty

| Sub-project | Relative difficulty | Why |
| --- | --- | --- |
| 3. Self-upload at session level | Easiest | No persistent knowledge base to manage, no ingestion pipeline, no long-term storage decisions — the file exists only for the current session |
| 1. RAG-based chatbot | Medium-to-hard | Requires a real ingestion pipeline (add/update/delete KB), a vector database, and — the hardest single piece in the whole project — the HITL feedback loop and "self-heal" behavior, which is a genuinely advanced pattern |
| 2. Database-based chatbot | Hardest | Natural-language-to-SQL generation is its own distinct skill, and it carries real safety concerns (a wrong or malicious generated query) that the other two sub-projects don't have |
| 4. Add visualization to data |  | When query give you response back, add visualization chat in other tab. |

This ranking directly drives the build order in Section 2 — start with the easiest, validate the core pattern (chat plus LLM plus a file/data source), then add complexity.

## 1.3  A Few Honest Flags Worth Knowing Before Starting

- The HITL/self-heal feature (1c) is the single most ambitious item in the entire brief. "Self-heal" can mean many different things in practice — from something simple (flag low-confidence answers for a human to review) to something genuinely research-grade (automatically retrain or re-rank retrieval based on feedback). The week-by-week plan below scopes this to a realistic, buildable MVP version, with the more advanced version noted as a stretch goal.

- The database chatbot (sub-project 2) needs a safety boundary from day one, not as an afterthought. A generated SQL query should run against a read-only database user, and ideally be validated (no DROP, no DELETE, a LIMIT enforced) before execution — this is scoped explicitly into its week rather than left implicit.

- "Build a CI/CD pipeline" and "deploy on AWS" are appropriately placed late in the plan, not early. Automating a deployment pipeline before there's a stable, working application to deploy is wasted setup — this mirrors the YAGNI principle from earlier in this series: build the thing first, automate its delivery once it's real.

# Section 2 — The Recommended Build Order, and Why

The full sequence, at a glance, before the detailed weekly breakdown:

- 1. Foundation — repo, FastAPI skeleton, basic JWT auth, Redis running, one manual deploy to prove the path works

- 2. Self-upload session chatbot (easiest sub-project) — validates the core chat-plus-LLM-plus-file pattern reused everywhere else

- 3. RAG chatbot — ingestion pipeline (add/update/delete KB) — the data layer, before the chat layer that depends on it

- 4. RAG chatbot — user Q&A over the KB — now the vector store has real data to query

- 5. RAG chatbot — HITL feedback loop / self-heal MVP — the hardest single feature, tackled last within sub-project 1, once the base RAG flow is solid

- 6. Database chatbot (NL2SQL) — the hardest sub-project overall, built once the team/you have two working chatbots' worth of pattern experience

- 7. Cross-cutting hardening — JWT enforced everywhere, Redis caching extended to all three, rate limiting

- 8. CI/CD pipeline — automate deployment now that there is a stable application to deploy

- 9. Logging, monitoring, observability — CloudWatch and LangSmith, wired into everything already built

- 10. Polish and stretch goals — resilience patterns, guardrails, final integration pass

## 2.1  Why This Order, Specifically

Easiest sub-project first, to validate the core pattern once, cheaply. The self-upload chatbot shares its fundamental shape (receive input, call the LLM, return a result) with both other sub-projects, but without the added complexity of a persistent knowledge base or a database safety boundary. Getting this working first proves the basic FastAPI-plus-LLM wiring is solid before adding harder pieces on top.

Data layer before the chat layer that depends on it, within RAG. There is no point building a polished chat UI over an empty vector store — the KB ingestion pipeline has to exist first, or there is nothing meaningful to query.

The hardest single feature (HITL/self-heal) is deliberately sequenced last within its own sub-project, once the simpler RAG Q&A flow is proven — this matches the YAGNI-adjacent instinct from earlier in this series: don't design the feedback loop against a system that doesn't reliably work yet.

The hardest sub-project overall (database chatbot) comes after both others are done, so the NL2SQL-specific challenges (schema awareness, query safety) are tackled with two working chatbots' worth of pattern experience already in hand, not as the very first thing attempted.

CI/CD and observability come after the application is functionally complete, not before — automating the deployment of something that doesn't work yet, or instrumenting monitoring for a system still being designed, is wasted setup effort that would likely need rework anyway.

# Section 3 — Week-by-Week Schedule

## Week 1 — Foundation

By end of week 1, you should have:

- A Git repository with a basic FastAPI project structure

- A single health-check endpoint (GET /health) that returns 200 OK

- Redis running locally via Docker, with the Python client library installed and a working set/get test

- Basic JWT authentication wired in — a login endpoint that issues a token, and one protected endpoint that requires it

- One manual deployment of this skeleton to AWS (a single EC2 instance or a basic ECS task is enough) — the goal is only to prove the deployment path works end to end, not to build real infrastructure yet

Goal of this week: prove every foundational piece (auth, cache, deployment) works in isolation before building real features on top of them.

## Week 2 — Self-Upload Session Chatbot

By end of week 2, you should have:

- A file upload endpoint (PDF, at minimum)

- Session-scoped storage — the uploaded file's content is available only for that session, not persisted long-term

- At least two working actions: "summarize this document" and "extract specific information from this document"

- The core LLM-calling pattern (prompt construction, calling the provider, returning the response) working end to end

Goal of this week: a complete, working sub-project — this is your first fully functional chatbot, even though it's the simplest one.

## Weeks 3-5 — RAG-Based Chatbot

### Week 3 — KB Ingestion Pipeline

- Backend endpoints for a developer to add, update, and delete a knowledge base

- Document chunking logic, and an embedding step feeding a vector store (Chroma, pgvector, or FAISS are all reasonable starting choices)

- Verify ingestion by directly querying the vector store and confirming chunks and embeddings look correct — before any chat UI exists on top of it

### Week 4 — User Q&A Over the KB

- A user-facing endpoint: take a question, retrieve relevant chunks, construct a prompt, call the LLM, return the answer

- Redis caching wired in here specifically — repeated questions should hit the cache, exactly the pattern already built and verified in Week 1

- Basic source attribution — track which KB document/chunk contributed to each answer, since this becomes important context for the feedback loop next week

### Week 5 — HITL Feedback Loop / Self-Heal MVP

- A feedback endpoint — thumbs up/down, or a short text comment, tied to a specific question-and-answer pair

- Store feedback with enough context to act on later: the question, the answer given, the source chunks used, and the user's feedback

- Scope the "self-heal" behavior to a realistic MVP: when a response receives negative feedback, flag it for review rather than attempting fully automatic correction. A simple, honest version: negative feedback marks that question as "needs review," and a developer-facing endpoint lists all flagged items. A more advanced version — automatically adjusting retrieval or re-ranking based on accumulated feedback — is a legitimate stretch goal, not a Week 5 requirement

## Week 6 — Database-Based Chatbot (NL2SQL)

By end of week 6, you should have:

- A semantic model or schema description passed to the LLM, so it understands the database's tables and columns

- A working prompt pattern that generates SQL from a natural-language question

- A safety boundary enforced before execution, non-negotiable from day one: the generated query runs against a read-only database user, is validated to block destructive statements (DROP, DELETE, UPDATE), and has a LIMIT enforced to prevent runaway result sets

- The query result converted back into a natural-language response

## Week 7 — Cross-Cutting Hardening

By end of week 7, you should have:

- JWT authentication enforced consistently across all three chatbots' endpoints, not just the Week 1 skeleton

- Redis caching extended to the self-upload and database chatbots where it makes sense (e.g., caching repeated database questions)

- Basic rate limiting per user, protecting LLM cost across all three sub-projects

## Week 8 — CI/CD Pipeline

By end of week 8, you should have:

- A GitHub Actions (or equivalent) workflow triggered on push to main

- The pipeline running tests, building a Docker image, and pushing it to a registry (ECR)

- Automatic deployment to AWS (ECS Fargate is a reasonable target, reusing the Deployment Paths pattern from earlier in this series) on a successful pipeline run

## Week 9 — Logging, Monitoring, and Observability

By end of week 9, you should have:

- Application logs flowing to CloudWatch

- LangSmith tracing wired into every LLM call across all three chatbots — prompts, responses, latency, and token usage all visible per request

- At least one basic dashboard or alert configured (e.g., alert on elevated error rate)

## Week 10 — Polish and Stretch Goals

By end of week 10, you should have:

- Timeouts and retries added to every LLM call (direct reuse of the Resilience Patterns document)

- A final integration pass — testing all three chatbots together under the same authentication and caching layer

- Any stretch goals from Section 4 selected and attempted, time permitting

# Section 4 — Good-to-Have Additions

Beyond the brief as given, these additions would meaningfully strengthen the project as a portfolio piece, each tagged with where it fits into the schedule and which document in this series it draws on.

| Addition | Fits into | Why it's worth adding |
| --- | --- | --- |
| Source citation in RAG answers | Week 4 | Showing which document/chunk an answer came from is a major trust and credibility feature for any RAG system, and it's already half-built once source tracking exists for the feedback loop in Week 5 |
| Streaming responses (Server-Sent Events) | Week 2 or Week 4 | Token-by-token streaming is standard UX for any modern chatbot, and directly reuses the streaming/buffering concepts from the Reverse Proxy document |
| "I don't know" fallback / confidence threshold | Week 4 | A RAG chatbot that confidently answers from irrelevant retrieved chunks is a common, credibility-damaging failure mode; a simple relevance-score threshold before answering is a direct application of graceful degradation from the Resilience Patterns document |
| Resilience patterns on every LLM call | Week 6 or Week 10 | Timeouts, retries with backoff, and a basic circuit breaker on LLM calls — direct reuse of the Resilience Patterns document, and a genuinely common gap in first-pass builds |
| Idempotency on KB update/delete | Week 3 | Prevents duplicate or corrupted KB entries if a request is retried — direct reuse of the Idempotency document |
| Multi-turn conversation memory | Week 2 or Week 4 | Remembering prior turns in the same session (not just answering each question in isolation) is a meaningful UX upgrade and a common client expectation |
| Multi-provider fallback (LLM Gateway pattern) | Week 10 (stretch) | If the primary LLM provider fails, automatically fall back to a secondary — direct reuse of the LLM Gateway document; a strong stretch goal, not a core requirement |
| A small evaluation harness (RAGAS-style) | Week 10 (stretch) | A handful of labeled question/answer pairs run automatically against the RAG chatbot to catch regressions — closes the evaluation gap flagged as a priority in the Complete Roadmap document |
| Admin dashboard for feedback and flagged items | Week 5 or Week 9 | A simple page listing negative-feedback items awaiting review turns the Week 5 self-heal MVP into something genuinely usable, not just a database table |
| Docker Compose for local development | Week 1 | Spin up the app, Redis, and the vector database together with one command — a small, high-value convenience for local development from the very start |

# Section 5 — A Light Note on Tech Stack Choices

Not prescriptive — any reasonable equivalent works — but a sensible, low-friction default stack for this project, drawing on choices already discussed throughout this series:

- Backend framework: FastAPI, run with Uvicorn (Server Terminology document)

- Vector store: Chroma or pgvector for local/early development; either scales reasonably for a portfolio-scale project without needing a managed vector DB service

- Relational database: PostgreSQL, both for the database chatbot's target data and for storing feedback/KB metadata

- Cache: Redis, exactly as already set up in Week 1

- LLM orchestration: LangChain for the RAG and database chatbots; LangGraph if the self-heal feedback loop grows into genuine multi-step agentic behavior

- Deployment target: ECS Fargate (Deployment Paths document) — a reasonable default balancing manageability and realistic production practice

- CI/CD: GitHub Actions — free, well-documented, integrates cleanly with ECR/ECS

# Closing Note

This document is the hands-on capstone companion to the theory-heavy System Design Study Series — nearly every week in this schedule directly reuses a pattern, decision, or correction already covered in an earlier document, listed throughout this plan for quick cross-reference.

## How to Use This Going Forward

- Treat each week's deliverable list as the actual definition of done, not a suggestion — resist the urge to add Section 4's good-to-haves before the corresponding week's core deliverable is genuinely working

- If a week runs long, it is far better to extend that week than to move on with a shaky foundation — Weeks 3-4 (the RAG ingestion and query pipeline) are the ones most likely to need extra time, since they carry the most technical risk

- This project, once complete, is a legitimate answer to "tell me about a GenAI system you've built" in any client or interview conversation — build it with that end use in mind, documenting decisions (why this vector store, why this safety boundary on the SQL chatbot) as you go, since that reasoning is often more valuable in conversation than the code itself

The one thing to carry into this build: start with the easiest working version of each piece, get it genuinely working end to end, and only then layer in the harder features — the same discipline behind YAGNI and KISS from earlier in this series, now applied to an entire project's sequencing, not just a single function.